## Backlog
Slice | Milestone | ID | Epic | Task | Description | Est (days) | Depends on | Sprint | Priority | Acceptance | Status
0 | Spine | T1.1 | 1 Supabase backend | Create Supabase project + dev env | Spin up project; configure env keys; install Supabase CLI; set up migrations folder. | 0.5 | - | A: Foundations | P0 | Prereq for AC3 | Not started
0 | Spine | T1.2 | 1 Supabase backend | Run Wave-1 schema | Apply vamo_wave1_schema.sql; verify tables, trip_balances view, is_trip_member() + join_trip() created. | 0.5 | T1.1 | A: Foundations | P0 | AC3 | Not started
0 | Spine | T1.3 | 1 Supabase backend | Configure auth providers | Enable email, Apple, Google, phone sign-in. | 1 | T1.1 | A: Foundations | P0 | Screen 1 | Not started
0 | Spine | T1.4 | 1 Supabase backend | Profile-creation trigger | On signup, trigger inserts profiles row; verify it fires. | 0.5 | T1.2;T1.3 | A: Foundations | P0 | Screen 1 | Not started
0 | Spine | T1.6 | 1 Supabase backend | RLS validation pass | Use Supabase RLS tester: confirm a non-member cannot read a trip. | 0.5 | T1.2 | A: Foundations | P0 | AC3 | Not started
0 | Spine | T2.1 | 2 Flutter app_core | Init Flutter monorepo | Set up app + app_core + feature_split packages (melos). | 0.5 | - | A: Foundations | P0 | Build order step 2 | Not started
0 | Spine | T2.2 | 2 Flutter app_core | Supabase client + session | Init client; session handling; secure token storage. | 0.5 | T2.1;T1.3 | A: Foundations | P0 | Screen 1 | Not started
0 | Spine | T2.3 | 2 Flutter app_core | Riverpod + router | Provider scaffolding + go_router navigation. | 0.5 | T2.1 | A: Foundations | P0 | - | Not started
0 | Spine | T2.4 | 2 Flutter app_core | Design system | Teal/sand theme, typography, core components, 'Si va?' styling. | 1 | T2.1 | A: Foundations | P0 | Brand | Not started
0 | Spine | T2.6 | 2 Flutter app_core | Analytics + entitlement stub | PostHog wrapper with the 7 events; wire entitlement check stub. | 0.5 | T2.1 | A: Foundations | P0 | AC6 | Not started
0 | Spine | T2.7 | 2 Flutter app_core | i18n setup | Externalize strings from the start. | 0.5 | T2.1 | A: Foundations | P0 | Non-functional | Not started
0 | Spine | T3.1 | 3 Auth + trips | Auth / onboarding screen | Continue with Apple/Google/email/phone wired to Supabase. | 1 | T2.2;T2.3;T1.3 | B: Core split flow | P0 | Screen 1; AC1,2 | Not started
0 | Spine | T3.2 | 3 Auth + trips | Trips list + empty state | List solo+group trips together; empty state is the 'Si va?' hook. | 1 | T2.5;T3.1 | B: Core split flow | P0 | Screen 2; AC1,2 | Not started
1 | Spine | T2.5 | 2 Flutter app_core | Drift local DB | Mirror trips, trip_members, expenses, expense_shares locally as UI source of truth. | 1 | T2.1 | A: Foundations | P0 | AC4 | Not started
1 | Spine | T3.3 | 3 Auth + trips | Create trip | Solo vs invite; name, destination, dates, base currency. Fire trip_created. | 1 | T3.2 | B: Core split flow | P0 | Screen 3; AC1,2,6 | Not started
1 | Spine | T4.1 | 4 Members + invite | Trip home hub | Tabs Expenses/Balances/Members; hide Balances for solo trips. | 1 | T3.3 | B: Core split flow | P0 | Screen 4 | Not started
2 | Spine | T5.1 | 5 Expenses + FX | Add expense screen | Amount+currency, payer, split equal/custom, description, category, date. | 1.5 | T4.1 | B: Core split flow | P0 | Screen 5; AC2 | Not started
2 | Spine | T5.2 | 5 Expenses + FX | Shares + invariant | Write expense_shares; enforce sum(share_cents)==base_cents on write. | 0.5 | T5.1 | B: Core split flow | P0 | AC2 | Not started
3 | Spine | T6.1 | 6 Balances + settle-up | settleUp() engine | Deterministic minimal-transaction settle-up, integer cents. | 0.5 | T2.1 | B: Core split flow | P0 | AC5 | Not started
3 | Spine | T6.2 | 6 Balances + settle-up | Settle-up unit tests | Fixtures: equal, custom, multi-payer, multi-currency, 3-person cycle. | 0.5 | T6.1 | B: Core split flow | P0 | AC5 | Not started
3 | Spine | T6.3 | 6 Balances + settle-up | Balances screen | Read trip_balances -> net per member; render minimal 'X pays Y' list. | 1 | T6.1;T5.2 | B: Core split flow | P0 | Screen 6; AC2 | Not started
4 | Spine | T6.4 | 6 Balances + settle-up | Mark settled + deep-links | settlements row status=marked, optimistic update, deep-link Venmo/PayPal/Wise prefilled. Fire settle_marked. | 1 | T6.3 | B: Core split flow | P0 | Screen 6; AC2,6 | Not started
4 | Spine | T6.5 | 6 Balances + settle-up | Confirm settlement | Recipient confirms (status=confirmed). Fire settle_confirmed. | 0.5 | T6.4 | B: Core split flow | P0 | AC2,6 | Not started
5 | Multiplayer | T4.2 | 4 Members + invite | Members tab + invite link | Insert invites row; share https://vamo.app/j/<token>. Fire member_invited. | 1 | T4.1 | B: Core split flow | P0 | Screen 7; AC6 | Not started
5 | Multiplayer | T4.3 | 4 Members + invite | Deep link + join_trip | If installed call join_trip(token) and open trip; else route to store keeping token. Fire invite_accepted. | 1 | T4.2 | B: Core split flow | P0 | AC2,6 | Not started
6 | Growth | T1.7 | 1 Supabase backend | FX rates daily cache | Edge function / scheduled fetch of exchangerate.host, cached once/day. | 0.5 | T1.1 | A: Foundations | P0 | AC5 | Not started
6 | Growth | T5.3 | 5 Expenses + FX | FX snapshot on expense | Non-base currency: fetch day rate, store base_cents + fx_rate + original. Fire expense_added. | 0.5 | T5.1;T1.7 | B: Core split flow | P0 | AC2,5,6 | Not started
7 | Growth | T1.5 | 1 Supabase backend | Storage buckets + signed URLs | Private buckets for avatars + snapshot images; signed-URL access policy. | 0.5 | T1.1 | A: Foundations | P0 | AC3 | Not started
7 | Growth | T7.1 | 7 Snapshot share | Compose snapshot card | Trip name, dates, total, avatars, teal/sand background, Vamo wordmark. | 1 | T2.4;T6.3 | C: Growth + ship | P0 | Screen 9; AC1 | Not started
7 | Growth | T7.2 | 7 Snapshot share | Rasterize + share | RenderRepaintBoundary -> PNG -> share sheet; upload to private bucket + signed URL. Fire snapshot_shared. | 0.5 | T7.1;T1.5 | C: Growth + ship | P0 | Screen 9; AC1,6 | Not started
8 | Growth | T8.1 | 8 Solo capture | Solo capture screen | Title, notes, photos; feeds the snapshot. | 1 | T4.1;T1.5 | C: Growth + ship | P0 | Screen 8; AC1 | Not started
9 | Hardening | T9.1 | 9 Offline + sync | Optimistic writes + sync worker | Queue writes; reconcile to Supabase, last-write-wins per field. | 1.5 | T2.5;T5.2 | C: Growth + ship | P0 | AC4 | Not started
9 | Hardening | T9.2 | 9 Offline + sync | Realtime per-trip channel | Subscribe per open trip so co-editors see live updates. | 0.5 | T9.1 | C: Growth + ship | P0 | Key flows | Not started
10 | Hardening | T10.1 | 10 Polish + ship | Settings screen | Display name, base currency, billing placeholder / entitlement check. | 0.5 | T3.1 | C: Growth + ship | P0 | Screen 10 | Not started
10 | Hardening | T10.2 | 10 Polish + ship | Empty + error states | Polish empty states ('Si va?'), error handling, microcopy. | 0.5 | T7.2;T8.1 | C: Growth + ship | P0 | Screen 2 | Not started
10 | Hardening | T10.3 | 10 Polish + ship | Analytics QA | Verify all 7 PostHog events fire correctly end-to-end. | 0.5 | T2.6 | C: Growth + ship | P0 | AC6 | Not started
10 | Hardening | T10.4 | 10 Polish + ship | RLS QA pass | Re-run RLS tester end-to-end across real flows. | 0.5 | T1.6 | C: Growth + ship | P0 | AC3 | Not started
10 | Hardening | T10.5 | 10 Polish + ship | Basic push notifications | Minimal push wiring. | 0.5 | T2.2 | C: Growth + ship | Stretch | Non-functional | Not started
10 | Hardening | T10.6 | 10 Polish + ship | Ship to TestFlight / Play internal | Build, sign, upload internal test tracks. | 0.5 | T10.2;T10.3;T10.4 | C: Growth + ship | P0 | Wave-1 done | Not started
11 | Signals | T11.1 | 11 Product signals | screen_viewed events | go_router observer fires screen_viewed with screen name on every navigation. | 0.25 | T2.6 | D: Signals | P1 | AC7 | Not started
11 | Signals | T11.2 | 11 Product signals | error/empty state events | AppErrorState fires error_shown (screen, kind); AppEmptyState fires empty_state_shown. | 0.25 | T2.6 | D: Signals | P1 | AC7 | Not started
11 | Signals | T11.3 | 11 Product signals | FlowTracker + flow_abandoned | Track add_expense/create_trip/invite flows; fire flow_abandoned with elapsed_ms on dispose-if-incomplete. | 0.5 | T2.6 | D: Signals | P1 | AC7 | Not started
11 | Signals | T11.4 | 11 Product signals | Intention doors (3) + notify me | plus/recap/map interest_tapped events on coming-soon doors; optional notify_me_opted_in sheet. Max 3 doors, clearly labelled. | 0.5 | T2.6;T10.1 | D: Signals | P1 | AC7 | Not started
11 | Signals | T11.5 | 11 Product signals | Suggest a feature | Apply 0006_suggestions.sql; Settings entry + form (text<=500, category); insert via repository; suggestion_submitted event (category only). | 0.5 | T1.2;T10.1 | D: Signals | P1 | AC7 | Not started
11 | Signals | T11.6 | 11 Product signals | Signals QA | All 8b events visible in PostHog; suggestions RLS verified (insert/read own only; non-owner blocked). | 0.25 | T11.1;T11.2;T11.3;T11.4;T11.5;T10.3 | D: Signals | P0 | AC7 | Not started
11 | Signals | T11.7 | 11 Product signals | action_failed event | Structured failure event on user-initiated writes: screen, action, kind, sanitized code (no raw exception text). Wire into create trip / add expense / settle / suggest catch blocks. | 0.25 | T2.6 | D: Signals | P1 | AC7 | Not started
12 | Themes | T12.1 | 12 Snapshot themes | Theme pack model + assets | ThemePack definition (bg, palette, typography accents) in app_core design; 5 packs: default teal/sand, ancient (Rome), beach, mountains, road trip. Watermark layer untouched and non-optional. | 0.5 | - | D: Signals | P1 | Growth loop | Not started
12 | Themes | T12.2 | 12 Snapshot themes | Keyword matcher | Map trip title/destination keywords to a pack (it/en keyword lists; fallback default). Pure function + unit tests. | 0.25 | T12.1 | D: Signals | P1 | Growth loop | Not started
12 | Themes | T12.3 | 12 Snapshot themes | Themed snapshot render + event | Snapshot card consumes matched pack; manual pack picker stub behind entitlement (premium later); fire snapshot_shared with theme property. | 0.5 | T12.1;T12.2 | D: Signals | P1 | Growth loop | Not started
13 | I18n | T13.1 | 13 I18n readiness | Directional layout audit | Sweep layouts: EdgeInsetsDirectional/AlignmentDirectional/start-end; directional icons. Watermark position deliberately fixed. | 0.5 | - | D: Signals | P1 | Non-functional | Not started
13 | I18n | T13.2 | 13 I18n readiness | Locale infrastructure | localizationsDelegates + supportedLocales (en,it + ar,he,zh,hi,ja,ru placeholders); dev RTL/pseudo-locale toggle. | 0.5 | T13.1 | D: Signals | P1 | Non-functional | Not started
13 | I18n | T13.3 | 13 I18n readiness | Bidi-safe money formatting | Unicode directional isolates around amounts in money_format + Arabic-context tests. Western digits for money everywhere. | 0.25 | - | D: Signals | P1 | Non-functional | Not started
13 | I18n | T13.4 | 13 I18n readiness | RTL goldens | Snapshot card + trip home + expenses under Directionality.rtl/ar; lock watermark mirroring decision. | 0.5 | T13.1;T13.2 | D: Signals | P1 | Non-functional | Not started
13 | I18n | T13.5 | 13 I18n readiness | Script smoke tests | CJK/Devanagari/Cyrillic render checks; Hindi digit grouping (lakh); locale dates. | 0.25 | T13.2 | D: Signals | P2 | Non-functional | Not started
13 | I18n | T13.6 | 13 I18n readiness | Safe error presentation sweep | showActionError helper in app_core: fires action_failed + shows catalogued message by kind (network/auth/server/unknown); replace ALL raw $e SnackBars and error texts (create trip, add expense, suggest, settings, trip home, join, capture, snapshot, members load); messages from i18n catalogue; debug builds may append sanitized code; lint/test guard that no UI string interpolates an exception. | 0.5 | T13.2 | D: Signals | P0 | Non-functional | Not started
[5 empty] | TOTAL effort (P0 + stretch) | 34.25

## Slice summary
Slice | Milestone | Demo outcome | Tasks | Effort (d) | Cumulative (d)
0 | Spine | Log in -> empty trips list | T1.1, T1.2, T1.3, T1.4, T1.6, T2.1, T2.2, T2.3, T2.4, T2.6, T2.7, T3.1, T3.2 | 8.5 | 8.5
1 | Spine | Create trip -> persists -> trip home | T2.5, T3.3, T4.1 | 3 | 11.5
2 | Spine | EUR30 dinner, equal split | T5.1, T5.2 | 2 | 13.5
3 | Spine | Who owes whom + tests green | T6.1, T6.2, T6.3 | 2 | 15.5
4 | Spine | Mark settle -> Venmo -> confirm | T6.4, T6.5 | 1.5 | 17
5 | Multiplayer | Second phone joins via link | T4.2, T4.3 | 2 | 19
6 | Growth | $ expense on EUR trip | T1.7, T5.3 | 1 | 20
7 | Growth | Share branded card | T1.5, T7.1, T7.2 | 2 | 22
8 | Growth | Solo capture -> snapshot | T8.1 | 1 | 23
9 | Hardening | Airplane mode + live co-edit | T9.1, T9.2 | 2 | 25
10 | Hardening | TestFlight / Play internal | T10.1, T10.2, T10.3, T10.4, T10.5, T10.6 | 3 | 28
11 | Signals | Friction + intention + suggestions visible | T11.1, T11.2, T11.3, T11.4, T11.5, T11.6, T11.7 | 2.5 | 30.5
12 | Themes | Trip title themes the share card | T12.1, T12.2, T12.3 | 1.25 | 31.75
13 | I18n | RTL-correct + script-ready (no translations yet) | T13.1-T13.6 | 2.5 | 34.25
|  |  | TOTAL | 34.25

## Sprint summary
Sprint | Focus | Tasks | Goal | Effort (d)
A: Foundations | Backend + app_core stood up | T1.1-T1.7, T2.1-T2.7 | Supabase live with schema+RLS+auth; Flutter shell with design system, Drift, analytics. | 0
B: Core split flow | The SplitTrip loop end-to-end | T3.1-T3.3, T4.1-T4.3, T5.1-T5.3, T6.1-T6.5 | Create/join trips, add multi-currency expenses, correct minimal settle-up, mark/confirm. | 0
C: Growth + ship | Snapshot, solo, offline, ship | T7.1-T7.2, T8.1, T9.1-T9.2, T10.1-T10.6 | Branded share + solo capture + offline sync; QA; ship to TestFlight / Play internal. | 0
|  |  | TOTAL | 0
Note: Sprints are rough capacity buckets. Use the Slice column on the Backlog as the day-to-day execution order.

## Acceptance coverage
# | Wave-1 'done' criterion | Covered by
AC1 | Solo user: create trip, capture, share branded snapshot | T3.2/T3.3, T8.1, T7.1/T7.2
AC2 | Group: invite/join (incl. mid-trip), custom-split multi-currency expenses, minimal settle-up, mark/confirm | T3.3, T4.2/T4.3, T5.1-T5.3, T6.3-T6.5
AC3 | Private by default, RLS-enforced (non-member can't read) | T1.2, T1.5, T1.6, T10.4
AC4 | Works offline, syncs on reconnect | T2.5, T9.1, T9.2
AC5 | Settle-up + FX math pass unit tests | T1.7, T5.3, T6.1, T6.2
AC6 | All analytics events fire | T2.6, T3.3, T4.2/T4.3, T5.3, T6.4/T6.5, T7.2, T10.3
AC7 | Product signals live: friction events, intention doors, suggestions (RLS-verified) | T11.1-T11.7